## Gantt Uaccess
Task Name | Duration | Start | Finish | Predecessors | Assigned To | % Complete | Status | Comments
Understanding requirements | 2d | 2023-01-02 | 2023-01-03
Negotiation with stakeholders | 2d | 2023-01-04 | 2023-01-05
Business contract | 4d | 2023-01-05 | 2023-01-10
Hiring of Program manager | 4d | 2023-01-10 | 2023-01-13
Hiring of procurement manager | 2w | 2023-01-13 | 2023-01-26
Hiring of tech lead | 2w | 2023-01-16 | 2023-01-27
Hiring of developers and testers | 2w | 2023-01-17 | 2023-01-30
Meeting with Procurement | 1d | 2023-01-29 | 2023-01-29
Gathering hardware | 8d | 2023-01-29 | 2023-02-07
Gathering licenses | 2d | 2023-02-07 | 2023-02-08
workstation and cable installations | 3d | 2023-02-08 | 2023-02-10
Team meeting with PM | 1d | 2023-02-10 | 2023-02-10
Team meeting with developers | 1d | 2023-02-10 | 2023-02-10
Backend Development | 45d | 2023-02-13 | 2023-04-14
Team meeting with tech lead | 1d | 2023-02-16 | 2023-02-16
Team meeting with tech lead | 1d | 2023-02-23 | 2023-02-23
Team meeting with tech lead | 1d | 2023-03-06 | 2023-03-06
UI Development | 30d | 2023-03-01 | 2023-04-11
Team meeting with tech lead | 1d | 2023-03-14 | 2023-03-14
Development of database | 5d | 2023-02-27 | 2023-03-03
Integrating | 5d | 2023-04-17 | 2023-04-21
Approvals | 1d | 2023-04-24 | 2023-04-24
Testing | 10d | 2023-04-24 | 2023-05-05
Team meeting | 1d | 2023-05-05 | 2023-05-05
Re development | 20d | 2023-05-08 | 2023-06-02
Integrating | 3d | 2023-06-05 | 2023-06-07
Re Testing | 5d | 2023-06-08 | 2023-06-14
Approvals | 3d | 2023-06-14 | 2023-06-16
Deployment | 1d | 2023-06-19 | 2023-06-19
Marketing | 7d | 2023-06-20 | 2023-06-28

## Comments
Row 1 | PHASE 1 : UNDERTAKING THE PROJECT | kunal sahjwani | 10/16/22 2:10 PM
Row 4 | PHASE 2 : TEAM GATHERING | kunal sahjwani | 10/16/22 2:10 PM
Row 9 | PHASE 3 | kunal sahjwani | 10/16/22 2:10 PM
Row 9 | PHASE 4 | kunal sahjwani | 10/16/22 2:09 PM
Row 12 | PHASE 4 : Explaining requirements | kunal sahjwani | 10/16/22 2:09 PM
Row 14 | PHASE 5 : DEVLOPMENT | kunal sahjwani | 10/16/22 2:09 PM
Row 14 | PHASE 5 : DEVELOPMENT | kunal sahjwani | 10/16/22 2:08 PM
Row 23 | PHASE 6 Testing | kunal sahjwani | 10/16/22 2:23 PM
Row 24 | Phase 7 Redevelopment | kunal sahjwani | 10/16/22 2:23 PM